Meeting of the City of Bloomsdale

January 11, 2022

The meeting was called to order at 7:00 PM with the following in attendance: Mayor Paul Monia, City Clerk Lynnette Randoll, Aldermen John Schweigert, Brandon Shortt, Chris Basler, and Monica Rozier. Also attending the meeting was John Lurk, Mark Evans with the Ste. Genevieve Herald and TJ Garb with Cochran.

The Meeting opened with the Pledge of Allegiance.

The minutes from the December Meeting were read and approved with a motion from Alderman Chris Basler, seconded by John Schweigert.

Alderman Brandon Shortt made a motion to pay all current expenditures, seconded by Monica Rozier. The motion was unanimously approved.

Overdue water bills were reviewed. Notices were sent Thursday, 01/06/2022.

TJ submitted a project status report for the elevated storage tank showing a notice to proceed date of March 1, 2022, for both Vern Bauman Contracting and Phoenix Fabricators, with a substantial completion date of November 30, 2022. Cochran is still waiting on contracts and bonds to be signed by both. A pre-construction meeting will be scheduled closer to March 1. He also submitted an updated project status report for the water distribution upgrade for replacement of 7,500 feet of water main, complete replacement of service line, service pits and service meters. Plans will be released to Contractors February 1, 2022, with a bid opening set for February 24. The project should be awarded March 8 with a notice to proceed scheduled April 1 and construction completion by July 31, 2022. Cochran met with John Lurk to verify the location of all existing water meters to be replaced during construction. Remaining water meters will be included in the design once topographic work is complete. TJ brought up procurement of pipe for the project as previously discussed. Mayor Monia will contact T. Drury Contracting to see if we can store pipe there if purchased now. The City would like for Cochran to bid out the pipe, giving Waterwork Specialties an opportunity to submit a bid. Alderman Basler also mentioned Jeff Sheehan with HD Supply as well as IMCO. TJ will contact John Lurk with pricing. Hopefully the 6” and 8” pipe will be available, as it has been hard to find.

Regarding the Clement Road upgrade, Dave Van Leer sent an email on January 7 stating that if the City intends to widen the street as planned, it would be most beneficial to hold off on upgrading the water main until a preliminary road improvement plan has been prepared and right-of-way needs identified. This will ensure future road work does not conflict with the new water main and allows for the City to obtain right-of-way for the road improvements and new water main simultaneously. The Mayor thinks the other upgrades are more pressing and the Council agreed. TJ will start on a plan to send to landowners. The Jersey Lane and St. Agnes Drive upgrades will proceed according to the submitted project status report and Clement Road will become a separate project. Alderman Schweigert inquired as to whether Clement Road will be widened on both sides of the street or just one, affecting the number of residents to be approached. Alderman Shortt thinks it would be a good idea to have a meeting with all affected residents at one time. Cochran will prepare the list of residents and documents. TJ left the meeting at 7:20 PM.

Clerk’s notes: The filings for Aldermen Basler and Schweigert were mailed on January 5, 2022. Ordinances were submitted to General Code for the annual Code Book update December 23, 2021. The Treatment Plant Permit Renewal was submitted, and the annual sludge report will be submitted with the Monthly Monitoring Report by the due date of January 31, 2022. A Company called Mastec is doing the installation of underground cable for Charter/Spectrum, and they have requested to buy bulk water from the City for the short duration of the project in City Limits. John Lurk will set this up and Clerk Randoll will bill accordingly.

Alderman Chris Basler made a motion to adjourn the meeting at 7:30 PM, seconded by Monica Rozier. The motion was approved.

__________________________________		______________________________

Mayor, Paul Monia						City Clerk, Lynnette Randoll